## Calendarul activităților en
The calendar of activities
related to the elaboration of the draft law on the unitary salary system in the budgetary sector
Name of stage/activity |  |  |  | 2017 | 2018 |  |  |  | 2019
Stage 1. Institutional Construction of the Unitary Salary System (USS) |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarterl IV | Quarter I
1.1. Creation of the Working Group (WG) on Post Evaluation
1.1.1. Selection of representative institutions
1.1.2. Requesting appointment of representatives in the Working Group
1.1.3. Setting up the working group
1.1.4. Elaborating the calendar of activities
1.1.5. Collaborating with a number of TA consultants in the work of the Working Group
1.2. Designation of the Technical Group (TG) of Evaluators
1.2.1. Requesting the appointment of representatives in the Group of Evaluators
1.2.2.. Selection of a number of local consultants
1.2.3.Establishing the Group of Evaluators
Stage 2. Assessing the Budget Sector Posts |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | QuarterI
2.1. Setting up the Register of Posts in the BS
2.2. Elaboration and approval of the evaluation methodology of the posts.
2.3. Training the members of the Group of Evaluators and the Working Group
2.4. Decisions on Occupational Groups, Evaluation Criteria, Data to be collected
2.5. Establishing the sample of representative posts
2.6. Organizing and conducting interviews with representative post holders
2.7. Elaboration of the database for evaluation of posts
2.8. Analysis of functions and matching them to the appropriate levels of the evaluation and relevance criteria
2.9. Calculation and approval of evaluation scores
2.10. Analyzing, scoring, reviewing, and ranking the posts evaluated
2.11. Proposals on the key elements of the pay scale
2.1 Decisions on the characteristics of the pay scale
2.13. Establishing pay grades, their composition and features
2.14. Assigning of the posts evaluated in the salary scale
2.15. Establishing rules on the transposition of professional advancement and promotion into the pay scale
2.16. Develop a simplified method for evaluating the rest of the Budget Sector.
2.17. Develop a simplified method for evaluation of the remaining posts in the Budget Sector
2.18. Simplified evaluation of the remaining posts in the Budget Sector
2.19. Assigning the remaining posts in the pay scale
2.20. Final report of the Working Group on post evaluation and final methodology applicable to the rest of the posts
Stage 3. Comparative Analysis of Salary Practices in the Budget Sector |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I
3.1. Evaluation of centrally available data (at function and institution level)
3.2. Establishing necessary data to be collected and the respondents
3.3. Requesting data about salary practices
3.4. Collecting data on salary practices
3.5. Processing, analyzing and building a database for simulations
3.6. Drawing up a Report on Salary Practices in the BS
Stage 4. Calculating the Impact in Different Public Policy Scenarios |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I
4.1. Calculate the impact of different salary policy scenarios
4.1.1 Communication of multiannual expenditure ceilings
4.1.2. Develop a complete nomenclature of bonuses, prizes, etc.
4.1.3 Establishment of salary components for all categories of staff
4.1.3. Elaboration of alternative proposals for salary scale, salary grades, salary increases, reference values (benchmarking), etc.
4.1.5. Testing alternatives and calculating their budget impact
4.1.6.Communicating results to social dialogue partners
4.2. Decisions on key elements of USS, based on post evaluation and impact analysis
Stage 5. Drafting the draft law on the unitary salary system in the budgetary sector |  |  |  | Quarter IV | Quarter I | Quarter II | QuarterIII | Quarter IV | Quarter I
5.1. Develop the draft law on USS
5.1.1.Establish all USS rules
5.1.2.Drafting the annexes to the draft law
5.1.3. Drafting the draft law
5.2 Completion of the draft law on the Unitary wage System in the Budgetary Sector
5.2.1. Public debate on the draft low
5.2.2. Presentation and approval of the low project by the Government
5.2.3. Debate and adoption of the low project by the Parliament
Stage 6. Implement the Law on the Unitary pay System in the Budgetary Sector |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I
6.1. Elaborating the normative framework for the implementation of the law
6.2. Elaboration and approval of the methodological norms to the law on the Unitary pay System in the Budgetary Sector
6.2.1.The methodology of classifying and re-positioning posts in payroll classes.
6.2.2.Methodology for assessing professional performance and their use in wage setting
6.2.3.Rules on bonuses and prizes
6.2.4.Rules on transitional measures until full implementation of the law
6.3. Training of personnel on the implementation of the Unitary pay System
Stage 7. Social dialogue to facilitate change in the Salary System |  |  |  | Quarter IV | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I
7.1. Identify the actors and factors that can support or oppose the new USS
7.2. Dissemination reports on the results of the technical steps (post evaluation, current salary practices, proposed new unitary salary system, budget impact)
7.3. Internal communication (with public institutions, trade unions, employees) and external (with the general public)
7.3.1. Communication of post evaluation results
7.3.2.Communication of key elements of the unitary salary system
Stage 8 .Information System for human resource management in the Budgetary Sector |  |  |  | Quarter VI | Quarter I | Quarter II | Quarter III | Quarter IV | Quarter I
8.1. Analysis and evaluation of existing staff and wage record systems
8.2. Analysis and evaluation of collected data
8.3. Description of budgeting processes for staff costs
8.4. Study on the requirements and implementation of a national information system on remuneration of work
8.5. Identifying the source of financing of the national information system on remuneration of work